## Sheet1
Task Name: (Dependencies top to bottom) | [8 empty] | Casey | Al ofi | Shaun | Al Hashemi | Total
|  |  | Role | Owner | Estimated | Effort | Actual | Actual | Actual | Actual | Actual | Actual
|  |  |  | (primary owner) (secondary owners) | By Task | Subtotals | By Task | Subtotals | By Task | By Task | By Task | By Task
Preliminary &
Parallel Tasks | Architecture |  |  |  |  | 12 |  | 12
|  | Design architecture | Project Manager | Casey, Al Ofi | 12 |  | 12 |  | 6 |  |  |  | 12
| Requirements |  |  |  |  | 9 |  | 10 |  |  |  |  | 0
|  | Gather | Requirements Engineer | Casey, Al Ofi | 2 |  | 3 |  | 2 | 1 |  |  | 3
|  | Analyze | Requirements Engineer | Casey, Al Ofi | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Specify | Requirements Engineer | Casey, Al Ofi | 3 |  | 3 |  | 1 | 2 |  |  | 3
| Documentation |  |  |  |  | 28 |  | 28 |  |  |  |  | 0
|  | Project Charter | Project Manager | Casey, Al Ofi | 2 |  | 2 |  | 1 | 1 |  |  | 2
|  | Release Plan | Project Manager | Al Ofi, Casey | 2 |  | 2 |  | 1 | 1 |  |  | 2
|  | Requirements Document | Project Manager, Requirements Engineer | Casey, Al Ofi | 5 |  | 5 |  | 3 | 2 |  |  | 5
|  | Project Plan | Project Manager, Developers | Casey, Al Ofi, Shaun, Al Hashemi | 5 |  | 5 |  | 1 | 1 | 1 | 1 | 5
|  | Architecture Document | Architect | Al Ofi, Casey | 4 |  | 4 |  | 2 | 2 |  |  | 4
|  | Test Report | Tester | Casey, Al Ofi | 8 |  | 8 |  | 2 | 6 |  |  | 8
|  | User Guide & System Admin Doc | Developers, Requirements Engineer | Casey, Al Ofi, Shaun, Al Hashemi | 2 |  | 2 |  | 0.5 | 0.5 |  | 1 | 2
0
Iteration 1: | Development |  |  |  |  | 29 |  | 20 |  |  |  |  | 0
|  | Determine technology needs | Developer | Shaun, Al Hashemi | 2 |  | 2 |  |  |  | 1 | 1 | 2
|  | Detrmine Physical Location Distances | Developer | Shaun, Al Hashemi | 5 |  | 5 |  |  |  | 3 | 2 | 5
|  | Detrmine Size Requirement per Office Location | Developer | Shaun, Al Hashemi | 7 |  | 5 |  |  |  | 3 | 2 | 5
|  | Research Routers Cost and Capabilities | Developer | Shaun, Al Hashemi | 15 |  | 8 |  |  |  | 4 | 4 | 8
| Analysis |  |  |  |  | 2 |  | 2 |  |  |  |  | 0
|  | Evaluate needs for next iteration | Project Manager | Casey, Al Ofi | 2 |  | 2 |  | 1 | 1 |  |  | 2
Iteration 2: | Development |  |  |  |  | 27 |  | 0
|  | Research Routers Cost and Capabilities | Developer | Casey, Al Ofi | 4
|  | Research the best options for web filters | Developer | Shaun, Al Hashemi | 5
|  | start bulding the model of the hospital network | Developer | Casey, Al Ofi, Shaun, Al Hashemi | 10
|  | start workin on the project prototype | Developer | Casey, Al Ofi, Shaun, Al Hashemi | 8
| Analysis |  |  |  |  | 6 |  | 0
|  | Evaluate needs for next iteration | Project Manager | Al Ofi, Casey | 6
Iteration 3: | Development |  |  |  |  | 0 |  | 0
|  | Review requirements | Developer
|  | Develop code for processing vendor locations | Developer
|  | Implement vendor map display | Developer
|  | Display vendor information | Developer
|  | Unit Testing | Developer
| Analysis |  |  |  |  | 0 |  | 0
|  | Acceptance Testing | Tester, Project Manager
|  | Bug fix as required | Tester, Developer
Total |  |  |  |  | 113 | 113 | 72 | 72 | 22.5 | 39.5 | 45 | 61.2 | 186.2